## Project Planner
Gizmoball Project Plan - Group MW1
[5 empty] | Current Week: | 6 |  |  | Plan Duration
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Weekly Progress Document (Group) | 1 | 1 | 2 | 3 | 100%
Git Setup (Group) | 1 | 1 | 1 | 1 | 100% | bar: WEEKS 1; WEEKS 3
Revised Specification (Tomas Šukevičius/Thomas Mclaughlin) | 1 | 3 | 1 | 3 | 100%
Use Cases (Thomas Mclaughlin) | 1 | 3 | 1 | 3 | 100%
Class Diagram (Greig Cairns/David T. Pocock) | 2 | 2 | 2 | 2 | 100% | bar: WEEKS 1; WEEKS 3
Class Descriptions (Group) | 3 | 1 | 3 | 1 | 100%
Screenshots of the GUI (Greig Cairns) | 1 | 2 | 1 | 2 | 100%
Physics Loop (David T. Pocock) | 1 | 3 | 1 | 3 | 100%
Triggering System (Chris Reilly) | 1 | 3 | 1 | 3 | 100%
Initial Project Plan (David T. Pocock) | 1 | 3 | 1 | 3 | 100%
Revised Class Diagram (David T. Pocock/Greig Cairns) | 4 | 3 | 4 | 3 | 100% | bar: WEEKS 4
Detail of Revision (David T. Pocock/Greig Cairns) | 5 | 2 | 5 | 2 | 100% | bar: WEEKS 4
Validation Testing Strategy (Chris Reilly/Tomas Šukevičius) | 4 | 3 | 4 | 3 | 100%
JUnit Testing Strategy Description (Tommy Mclaughlin/Chris Reilly) | 5 | 2 | 5 | 2 | 100%
Updated Project Plan (Greig Cairns) | 4 | 3 | 4 | 3 | 100%
Prototype 1 Implementation (Absorber) (Chris Reilly) | 4 | 3 | 4 | 3 | 100%
Prototype 2 Implementation (Collisions) (David T. Pocock) | 4 | 3 | 4 | 3 | 100%
Prototype 3 Implementation (Load Board) (Greig Cairns) | 4 | 3 | 4 | 3 | 100%
Prototype 4 Implementation (Flipper) (Thomas Mclaughlin) | 4 | 3 | 4 | 3 | 100%
Physics package integration David T. Pocock) | 3 | 1 | 3 | 1 | 100%
JUnit Testing (Tomas Šukevičius) | 7 | 4 | 7 | 4 | 100%
Debugging (Group) | 6 | 5 | 6 | 5 | 100%
Project Finalisation (Group) | 10 | 1 | 10 | 1 | 100%
Preparation for demo (Group) | 10 | 1 | 10 | 1 | 100%
| 0 | 0 | 0 | 0 | 100%
Model | 0 | 0 | 0 | 0 | 100%
Ball (David T. Pocock) | 3 | 5 | 3 | 5 | 100%
CircleBumper (David T. Pocock) | 3 | 5 | 3 | 5 | 100%
SquareBumper (David T. Pocock) | 3 | 5 | 3 | 5 | 100%
TriangleBumper (David T. Pocock) | 3 | 5 | 3 | 5 | 100%
LFlipper (Thomas Mclaughlin) | 3 | 6 | 3 | 6 | 100%
Rflipper (Thomas Mclaughlin) | 3 | 6 | 3 | 6 | 100%
Collisions (David T. Pocock) | 3 | 5 | 3 | 5 | 100%
Absorber (Chris Reilly) | 3 | 6 | 3 | 6 | 100%
GizmoConnection (Tomas Šukevičius, Chris Reilly, Thomas Mclaughlin) | 7 | 2 | 7 | 2 | 100%
Key Connection (Tomas Šukevičius, Chris Reilly, Thomas Mclaughlin) | 6 | 2 | 6 | 2 | 100%
Save (Greig Cairns) | 7 | 2 | 7 | 2 | 100%
Load (Greig Cairns) | 7 | 3 | 7 | 3 | 100%
LoadBuild (Greig Cairns) | 3 | 5 | 3 | 5 | 100%
Model (Greig Cairns, David T.Pocock) | 3 | 8 | 3 | 8 | 100%
Walls (Greig Cairns) | 3 | 1 | 3 | 1 | 100%
| 0 | 0 | 0 | 0 | 100%
View | 0 | 0 | 0 | 0 | 100%
Board (Greig Cairns, David T.Pocock) | 3 | 6 | 3 | 6 | 100%
BuildBoard (Greig Cairns) | 3 | 1 | 3 | 1 | 100%
PlayBoard (Greig Cairns, David T.Pocock) | 3 | 1 | 3 | 1 | 100%
BuildGUI (Greig Cairns) | 3 | 4 | 3 | 4 | 100%
PlayGUI (Greig Cairns) | 3 | 4 | 3 | 4 | 100%
IGUI (David T.Pocock) | 6 | 3 | 6 | 3 | 100%
| 0 | 0 | 0 | 0 | 100%
Controller | 0 | 0 | 0 | 0 | 100%
AddAbsorberL (Chris Reilly) | 6 | 2 | 6 | 2 | 100%
AddBallL (David T.Pocock) | 6 | 2 | 6 | 2 | 100%
AddCircleBumperL (David T.Pocock) | 6 | 2 | 6 | 2 | 100%
AddSquareBumperL (David T.Pocock) | 6 | 2 | 6 | 2 | 100%
AddTriangleBumperL (David T.Pocock) | 6 | 2 | 6 | 2 | 100%
AddLFlipperL (Thomas Mclaughlin) | 6 | 2 | 6 | 2 | 100%
AddRFlipperL (Thomas Mclaughlin) | 6 | 2 | 6 | 2 | 100%
MoveGizmoL (David T.Pocock) | 3 | 1 | 3 | 1 | 100%
RotateGizmoL (David T.Pocock) | 3 | 1 | 3 | 1 | 100%
DeleteGizmoL (Greig Cairns) | 3 | 1 | 3 | 1 | 100%
ClearBoardL (Greig Cairns) | 3 | 1 | 3 | 1 | 100%
ConnectGizmoL (Tomas Šukevičius, Chris Reilly) | 8 | 2 | 8 | 2 | 100%
DisconnectGizmoL (Tomas Šukevičius,Thomas Mclaughlin) | 8 | 2 | 8 | 2 | 100%
KeyConnectGizmoL (Chris Reilly, Thomas Mclaughlin) | 8 | 2 | 8 | 2 | 100%
KeyDisconnectGizmoL (Chris Reilly, Thomas Mclaughlin) | 8 | 2 | 8 | 2 | 100%
FrictionL (David T.Pocock) | 8 | 3 | 8 | 3 | 100%
GravityL (Greig Cairns) | 8 | 3 | 8 | 3 | 100%
LoadL (Greig Cairns) | 6 | 2 | 6 | 2 | 100%
SaveL (Greig Cairns) | 8 | 2 | 8 | 2 | 100%
ExitL (Greig Cairns) | 6 | 1 | 6 | 1 | 100%
StartL (David T.Pocock) | 4 | 3 | 4 | 3 | 100%
PauseL (David T.Pocock) | 4 | 3 | 4 | 3 | 100%
TickL (David T.Pocock) | 4 | 3 | 4 | 3 | 100%
ReloadL (Greig Cairns) | 8 | 2 | 8 | 2 | 100%
SwitchToBuildModeL (Chris Reilly, Thomas Mclaughlin) | 9 | 2 | 9 | 2 | 100%
SwitchToPlayModeL (Chris Reilly, Thomas Mclaughlin) | 9 | 2 | 9 | 2 | 100%
Testing
Junit Testing (Tomas Šukevičius, rest of group when required) | 6 | 5 | 6 | 5 | 100%