## Project Planner
Gizmoball Project Plan - Group MW1
[5 empty] | Current Week: | 3 |  |  | Plan Duration
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Weekly Progress Document (Group) | 1 | 1 | 2 | 3 | 100%
Git Setup (Group) |  |  |  |  | 100% | bar: WEEKS 1; WEEKS 3
Revised Specification (Tomas Šukevičius/Thomas Mclaughlin) | 1 | 3 | 1 | 3 | 100%
Use Cases (Thomas Mclaughlin) | 1 | 3 | 1 | 3 | 100%
Class Diagram (Greig Cairns/David T. Pocock) | 2 | 2 | 2 | 2 | 100% | bar: WEEKS 1; WEEKS 3
Class Descriptions (Group) | 3 | 1 | 3 | 1 | 100%
Screenshots of the GUI (Greig Cairns) | 1 | 2 | 1 | 2 | 100%
Physics Loop (David T. Pocock) | 1 | 3 | 1 | 3 | 100%
Triggering System (Chris Reilly) | 1 | 3 | 1 | 3 | 100%
Initial Project Plan (David T. Pocock) | 1 | 3 | 1 | 3 | 100%
Model Implementation (David T. Pocock/Thomas Mclaughlin) | 4 | 7 | 4 | 7 | 100%
View Implementation (Greig Cairns) | 4 | 7 | 4 | 7 | 100%
Controller Implementation (Chris Reilly/Tomas Šukevičius) | 4 | 7 | 4 | 7 | 100%
Revised Class Diagram (David T. Pocock/Greig Cairns) | 4 | 3 | 4 | 3 | 100%
Detail of Revision (Thomas Mclaughlin) | 5 | 2 | 5 | 2 | 100%
Class Specification (Thomas Mclaughlin) | 6 | 1 | 6 | 1 | 100%
Validation Testing Strategy (Chris Reilly/Tomas Šukevičius) | 4 | 3 | 4 | 3 | 100%
JUnit Testing Strategy Description (Tomas Šukevičius/Chris Reilly) | 5 | 2 | 5 | 2 | 100%
Updated Project Plan (David T. Pocock) | 4 | 3 | 4 | 3 | 100%
Prototype 1 Implementation (Absorber) (Chris Reilly) | 5 | 2 | 5 | 2 | 100%
Prototype 2 Implementation (Collisions) (David T. Pocock) | 3 | 2 | 3 | 2 | 100%
Prototype 3 Implementation (Load Board) (Greig Cairns) | 5 | 2 | 5 | 2 | 100%
Prototype 4 Implementation (Flipper) (Thomas Mclaughlin) | 3 | 2 | 3 | 2 | 100%
Physics package integration David T. Pocock) | 3 | 1 | 3 | 1 | 100%
JUnit Testing (Tomas Šukevičius) | 4 | 7 | 4 | 7 | 100%
Debugging (Group) | 6 | 5 | 6 | 5 | 100%
Project Finalisation (Group) | 10 | 1 | 10 | 1 | 100%
Preparation for demo (Group) | 10 | 1 | 10 | 1 | 100%